## README
RADIANT-MVT™ TRADING MODULE ¦ DEVELOPMENT BACKLOG
Source: AI Trading Intelligence Blueprint for INEOS (Caliche Energy Solutions, May 2026)
PURPOSE
This workbook translates the INEOS Trading AI deck into a prioritized engineering backlog the Caliche dev team
can execute against. 45 epics across 5 architecture layers and 5 delivery phases. Built to map directly to the
deck's 5-layer AI Orchestration framework and the 90-day pilot path with INEOS Trading & Shipping.
HOW TO USE
• BACKLOG tab — Full prioritized epic list — filter, sort, assign owners, paste into Jira. Each row is one epic.
• PHASES tab — Phase-by-phase rollup showing what ships when, with the day-range and a summary deliverable.
• BY LAYER tab — Architecture-layer rollup — Layer 1 through Layer 5 + cross-cutting platform work.
• DASHBOARD tab — Live counts by priority, phase, layer, workstream. Auto-updates as Status column changes.
CONVENTIONS
• Priority: P0 = critical / blocking · P1 = high · P2 = medium · P3 = nice-to-have
• Phase: 1 - Foundation (days 1-30) · 2 - Pilot (31-60) · 3 - Scale (61-90) · 4 - Harden (91-180) · 5 - Expansion (180+)
• Layer: L1 Data Collection · L2 Data Lake · L3 Analytics Engine · L4 AI/ML Models · L5 BI · X Cross-Cutting
• Effort: S = ~1 week · M = 2-4 weeks · L = 1-2 months · XL = 2-3 months (one team, full-time)
• Status: Backlog · In Progress · In Review · Done · Blocked
• ID format: RMVT-T-NNN (Radiant-MVT Trading, sequential)
AT A GLANCE
• Total epics | 45
• P0 (critical) | 12
• P1 (high) | 14
• P2 (medium) | 12
• P3 (low) | 7
• Phase 1 (days 1-30) | 9
• Phase 2 (days 31-60) | 7
• Phase 3 (days 61-90) | 10
• Phase 4 (days 91-180) | 12
• Phase 5 (180+) | 7
CALICHE ENERGY SOLUTIONS · RADIANT-MVT™ TRADING MODULE · www.calichesolutions.com

## BACKLOG
RADIANT-MVT™ TRADING MODULE · BACKLOG
ID | Priority | Phase | Layer | Workstream | Epic | Description | Acceptance Criteria | Effort | Dependencies | Status | Owner | Notes
RMVT-T-001 | P0 | 1 - Foundation | X - Cross-Cutting | Platform/Infra | Trading-Module API Gateway | Stand up the trading-module API surface: auth, rate limiting, tenant routing, request/response logging. All trading-module services consumed via this gateway. | OAuth2 + service-account auth working; per-tenant rate limits enforced; 99.95% uptime in load test; OpenAPI spec published. | L | — | Backlog
RMVT-T-002 | P0 | 1 - Foundation | X - Cross-Cutting | Platform/Infra | Multi-Tenant Data Isolation for Trading Workspaces | Trading data is highly sensitive. Build hard tenant boundaries (row-level + storage-level) so one trading-floor's data is never queryable by another. | Per-tenant encryption keys; row-level security tested by red-team; audit log of every cross-boundary attempt. | L | RMVT-T-001 | Backlog
RMVT-T-003 | P0 | 1 - Foundation | X - Cross-Cutting | Platform/Infra | TagTrack™ Extension for Trading Instruments | Extend molecular tagging from physical commodities to financial instruments: every paper trade, futures contract, swap, and option receives an immutable Radiant-MVT ID linked to its physical-equivalent molecules. | Every trade booked in pilot has a TagTrack ID; ID survives amendments/novations; chain-of-custody trace from physical lift to paper hedge passes audit. | XL | RMVT-T-002 | Backlog
RMVT-T-004 | P0 | 1 - Foundation | X - Cross-Cutting | Platform/Infra | Audit Trail & Lineage Framework | Immutable, append-only audit log for every read/write/calc on trading data. Required for Dodd-Frank, EMIR, REMIT compliance. | Every position change traceable to its origin tick; auditor can replay any P&L number from raw inputs; tamper-evident hashes verified. | L | RMVT-T-002 | Backlog
RMVT-T-005 | P0 | 1 - Foundation | L1 - Data Collection | Connectors | RightAngle Position & Trade Connector | Real-time pull of positions, trades, amendments, and physical schedules from ION RightAngle. Leverage Caliche's founding-era RightAngle knowledge. | Live trade feed <2s latency; handles novations/amendments idempotently; reconciles to RightAngle's own EOD reports at 99.5%+. | L | RMVT-T-003 | Backlog
RMVT-T-006 | P0 | 1 - Foundation | L1 - Data Collection | Connectors | Platts & Argus Market Data Connector | Pricing curves, indices, settlements from Platts and Argus. Includes historical backfill and intraday updates. | All commodity curves used by pilot book ingested; intraday refresh on settlement events; 10-year historical backfill complete. | M | RMVT-T-001 | Backlog
RMVT-T-007 | P0 | 1 - Foundation | L2 - Data Lake | Data Platform | Time-Series Store for Curves, Vols & Settlements | Purpose-built TSDB for trading market data — fast slice by tenor, basis, region, commodity, vol point. | 1B+ data points indexed; sub-100ms range queries; supports versioned curves (rebuilt vs. original). | L | RMVT-T-001 | Backlog
RMVT-T-008 | P0 | 1 - Foundation | L2 - Data Lake | Data Platform | Trade Blotter Store with Full Lineage | Every trade — booking, amendment, novation, termination — stored as an immutable event log with state-rebuild capability. | Any historical position state reconstructible from event log; amendments traceable to user, system, timestamp; complete trade lifecycle queryable. | L | RMVT-T-003 | Backlog
RMVT-T-009 | P0 | 1 - Foundation | L2 - Data Lake | Data Platform | Position History Store with Molecule Indexing | Position snapshots keyed by TagTrack ID — every physical, paper, and exchange position queryable down to the molecule. | Position-by-molecule queries return <500ms; reconciles to ETRM EOD; integrates with TagTrack lineage. | L | RMVT-T-003, RMVT-T-008 | Backlog
RMVT-T-010 | P0 | 2 - Pilot | L3 - Analytics Engine | Analytics | Real-Time P&L Engine (Pilot Book) | Intraday MTM and P&L attribution for the pilot commodity book — by trader, lane, molecule, strategy. | P&L refresh <5s on market data tick; attribution sums to total; matches T+1 settlement P&L within tolerance. | L | RMVT-T-007, RMVT-T-009 | Backlog
RMVT-T-011 | P0 | 2 - Pilot | L3 - Analytics Engine | Analytics | Position Aggregation Service | Consolidate physical + paper + exchange positions into a single net view per commodity, region, tenor. | Net position matches sum of constituents; handles cross-commodity offsets; updates within 5s of trade booking. | M | RMVT-T-005, RMVT-T-009 | Backlog
RMVT-T-012 | P0 | 2 - Pilot | X - Cross-Cutting | Data Platform | Physical-to-Financial Reconciliation Engine | Real-time reconciliation between physical operations data (lifts, transfers, inventory) and financial system positions — the core trust layer. | 98.5%+ auto-match rate; exceptions surfaced with root-cause hints; replaces the T+1 spreadsheet reconciliation process. | XL | RMVT-T-009, RMVT-T-011 | Backlog
RMVT-T-013 | P1 | 2 - Pilot | L4 - AI/ML Models | ML Models | Optimal Hedging Recommendation Model (First AI Use Case) | First production AI model — recommends hedge structures against physical length on pilot book. Trained on Radiant-MVT-reconciled data with full lineage. | Backtested vs. desk decisions on 12-mo history; explainability output for every recommendation; trader-in-the-loop approval workflow. | L | RMVT-T-010, RMVT-T-011 | Backlog
RMVT-T-014 | P1 | 2 - Pilot | L4 - AI/ML Models | ML Models | Model Lineage & Explainability Framework | Cross-cutting capability — every AI output traceable to its inputs, model version, training data snapshot. Required for trader trust and audit. | SHAP/LIME outputs for every model; model registry tracks version-to-prediction linkage; auditor can reproduce any historical prediction. | L | RMVT-T-004, RMVT-T-013 | Backlog
RMVT-T-015 | P1 | 2 - Pilot | L5 - Business Intelligence | UX | Trader Desk Dashboard v1 | Live P&L, position heat-map, AI hedge recommendations, exposure-by-molecule. Designed for trader-speed decisions, not after-hours review. | Loads <2s; updates real-time on tick; pilot traders complete 5 standard workflows in <30s each. | L | RMVT-T-010, RMVT-T-013 | Backlog
RMVT-T-016 | P1 | 2 - Pilot | L5 - Business Intelligence | UX | Pre-Trade Margin & Credit Check UI | Before-the-click margin requirement, counterparty exposure check, and credit-line availability — surfaced inline at trade entry. | Check completes <1s; integrates with counterparty master; blocks trades exceeding limits with override workflow. | M | RMVT-T-015 | Backlog
RMVT-T-017 | P1 | 3 - Scale | L1 - Data Collection | Connectors | Endur Position & Trade Connector | Extend ETRM connector framework to OpenLink Endur — same lineage and event-log semantics as RightAngle connector. | Feature-parity with RightAngle connector; cross-ETRM trade dedup logic verified on test cases. | M | RMVT-T-005 | Backlog
RMVT-T-018 | P1 | 3 - Scale | L1 - Data Collection | Connectors | Allegro Position & Trade Connector | Extend ETRM connector framework to Allegro — same lineage and event-log semantics. | Feature-parity with RightAngle connector; tested against Allegro 8.x and 9.x. | M | RMVT-T-005 | Backlog
RMVT-T-019 | P1 | 3 - Scale | L1 - Data Collection | Connectors | ICE & NYMEX Direct Exchange Connector | FIX-protocol direct exchange connectivity for executed trades, drop-copy, and clearing. | FIX 4.4/5.0 certified; drop-copy reconciles to clearing statement; sub-second trade capture. | L | RMVT-T-001 | Backlog
RMVT-T-020 | P1 | 3 - Scale | L1 - Data Collection | Connectors | Bloomberg Market Data Connector | Bloomberg B-PIPE / Server API integration — pricing, curves, vol surfaces, news headers. | B-PIPE feed live; entitlement compliance verified; supports Bloomberg formula library for custom curves. | M | RMVT-T-006 | Backlog
RMVT-T-021 | P1 | 3 - Scale | L3 - Analytics Engine | Analytics | VaR Engine (Parametric + Historical Simulation) | Two VaR methodologies live, configurable per book. Foundation for stress testing and middle-office risk reporting. | Daily VaR matches backtest within tolerance; supports 1d/10d horizons; configurable confidence intervals. | L | RMVT-T-011 | Backlog
RMVT-T-022 | P1 | 3 - Scale | L3 - Analytics Engine | Analytics | Curve Construction Service | Smoothed forwards, basis differentials, vol surfaces — built from market data, model-ready for downstream AI. | Curves rebuild on settlement events <30s; matches reference curves within tolerance; available via API for ML training. | M | RMVT-T-007 | Backlog
RMVT-T-023 | P1 | 3 - Scale | L4 - AI/ML Models | ML Models | Anomaly Detection — Fat-Finger & Rogue Trade Surveillance | ML model flags suspicious entries pre- and post-trade: fat-finger size, unusual P&L moves, off-market prices, rogue patterns. | False-positive rate <5% on backtest; surfaces 100% of seeded test anomalies; alerts route to surveillance dashboard. | L | RMVT-T-010, RMVT-T-014 | Backlog
RMVT-T-024 | P1 | 3 - Scale | L5 - Business Intelligence | UX | Middle Office & Risk Dashboard | Real-time VaR, counterparty exposure, limit breaches, anomaly alerts, audit lineage views. | Risk team completes 5 standard workflows; alert escalation tested; limit breach drill-down to trade level. | L | RMVT-T-021, RMVT-T-023 | Backlog
RMVT-T-025 | P1 | 3 - Scale | L2 - Data Lake | Data Platform | Contract & Confirmation Corpus + Vectorization | Every trade confirmation, ISDA, master agreement ingested, parsed, and embedded for retrieval by the GenAI Copilot. | 100% of pilot-book contracts indexed; semantic search returns relevant clauses; supports natural-language queries. | L | RMVT-T-008 | Backlog
RMVT-T-026 | P1 | 3 - Scale | L4 - AI/ML Models | ML Models | GenAI Trade Copilot v1 (RAG) | Natural-language interface over positions, contracts, market data — 'what's my exposure if Urals widens 50¢' returns an answer with citations. | Answers cite source data; latency <5s for common queries; hallucination rate <2% on eval set. | L | RMVT-T-025, RMVT-T-014 | Backlog
RMVT-T-027 | P2 | 4 - Harden | L3 - Analytics Engine | Analytics | Monte Carlo VaR & Stress Testing Framework | Add Monte Carlo VaR alongside parametric/historical. Configurable stress scenarios (historical event replay, hypothetical shocks). | MC VaR converges in <60s for pilot books; canned scenarios (2008, 2014 oil crash, 2020 COVID, 2022 Russia) ship with system. | L | RMVT-T-021 | Backlog
RMVT-T-028 | P2 | 4 - Harden | L3 - Analytics Engine | Analytics | Greeks Calculator (Delta / Gamma / Vega / Theta) | Option Greeks on demand for the desk — vanilla, average-price, and spread structures. | Greeks match analytical benchmark for vanilla options; AAD/finite-difference for path-dependent; available via API and dashboard. | M | RMVT-T-022 | Backlog
RMVT-T-029 | P2 | 4 - Harden | L3 - Analytics Engine | Analytics | Settlement Engine — Lifts, Invoicing, Demurrage, FX | Physical lift reconciliation, invoice generation, demurrage tracking, FX settlement — all tied to TagTrack lineage. | Auto-generates invoices from physical lift events; demurrage clock auto-starts/stops; FX settlement matches treasury reports. | L | RMVT-T-009, RMVT-T-012 | Backlog
RMVT-T-030 | P2 | 4 - Harden | L3 - Analytics Engine | Analytics | Regulatory Reporting — Dodd-Frank, EMIR, REMIT | Auto-generated reporting from immutable trade lineage. Replaces weeks of manual prep with continuous export. | Reports validate against current regulator schemas; 75% reduction in compliance team prep time vs. baseline. | L | RMVT-T-004, RMVT-T-008 | Backlog
RMVT-T-031 | P2 | 4 - Harden | L4 - AI/ML Models | ML Models | Forecasting Models — Forward Curves, Basis, Vol | ML-driven curve evolution and basis prediction — feeds pre-trade analytics and mark-to-model. | Out-of-sample MAPE beats baseline persistence model by 20%+; backtested over 24mo; explainability per forecast. | L | RMVT-T-022 | Backlog
RMVT-T-032 | P2 | 4 - Harden | L4 - AI/ML Models | ML Models | Trade Idea Generation Engine | Pattern recognition over historical spreads, arbs, seasonal plays — surfaces ideas with rationale, not as black-box signals. | Backtested PnL beats benchmark; every idea has plain-English rationale; trader feedback loop captured for retraining. | L | RMVT-T-031, RMVT-T-014 | Backlog
RMVT-T-033 | P2 | 4 - Harden | L2 - Data Lake | Data Platform | Counterparty Master Data Service | Single source for legal entities, ISDAs, credit lines, settlement instructions — referenced by every other service. | Pilot-book counterparties fully modeled; KYC/AML metadata captured; credit-line aggregation across legal entities. | M | RMVT-T-008 | Backlog
RMVT-T-034 | P2 | 4 - Harden | L1 - Data Collection | Connectors | News & Sentiment Feed Integration | Wire services, regulatory filings, refinery/pipeline outages, OPEC actions — tagged to commodities, regions, counterparties. | All headlines auto-tagged with commodity/region/entity in <30s; deduplication across sources; sentiment score per headline. | M | RMVT-T-001 | Backlog
RMVT-T-035 | P2 | 4 - Harden | L1 - Data Collection | Connectors | AIS / Vessel Tracking Connector | Live AIS vessel data — origin, destination, ETA, cargo type. Feeds physical-leg tracking and logistics-optimization use cases. | Pilot book's chartered vessels visible in real-time; ETA delta to nomination flagged; integrates with TagTrack for cargo lineage. | M | RMVT-T-001 | Backlog
RMVT-T-036 | P2 | 4 - Harden | L4 - AI/ML Models | ML Models | Event & Sentiment Impact Scoring Model | News + outage events scored against the position book — early warning when exposure profile changes. | Auto-correlates events to position deltas; precision/recall validated on historical event set; integrates with Trader Dashboard alerts. | L | RMVT-T-034, RMVT-T-031 | Backlog
RMVT-T-037 | P2 | 4 - Harden | L5 - Business Intelligence | UX | C-Suite Executive Briefing (GenAI-Generated) | Daily natural-language briefing of trading floor status, key P&L drivers, top risks. Auto-generated from reconciled data. | Briefing generated <2min after EOD close; matches manual briefing on key facts; tone configurable (terse / narrative). | M | RMVT-T-026, RMVT-T-010 | Backlog
RMVT-T-038 | P2 | 4 - Harden | X - Cross-Cutting | Platform/Infra | Alert Routing & Escalation Engine | Configurable alert routing — desk alerts to trader, risk breaches to CRO, regulatory exceptions to compliance. | Routing rules configurable in UI; supports email/Slack/Symphony/MS Teams; escalation chains tested. | M | RMVT-T-023, RMVT-T-024 | Backlog
RMVT-T-039 | P3 | 5 - Expansion | L1 - Data Collection | Connectors | Voice & Chat Capture (Bloomberg IB, Symphony, Teams) | Real-time capture of trader communications for compliance, idea mining, and AI copilot context. | All channels captured to retention store; transcription within 5min; entitlements verified before storage. | L | RMVT-T-002 | Backlog
RMVT-T-040 | P3 | 5 - Expansion | L2 - Data Lake | Data Platform | Voice-to-Text & Transcript Vectorization | Convert captured voice/chat to searchable, vectorized transcripts feeding GenAI Copilot and surveillance models. | WER <8% on trading-floor vocabulary; transcripts vectorized + retrievable; speaker diarization for multi-party calls. | L | RMVT-T-039 | Backlog
RMVT-T-041 | P3 | 5 - Expansion | L5 - Business Intelligence | UX | Trader Annotation & Rationale Capture | Lightweight UI for traders to log hedge intent, market view, and reasoning at trade entry — fuels future AI training. | <10s to log; annotations searchable; surfaces in P&L attribution and copilot context. | M | RMVT-T-015 | Backlog
RMVT-T-042 | P3 | 5 - Expansion | L4 - AI/ML Models | ML Models | Model Lifecycle Management (MLOps) | Standing capability for model retraining, A/B testing, drift detection, rollback. Required as model count grows. | Automated retraining triggers; drift alerts on production models; one-click rollback to previous version. | L | RMVT-T-014 | Backlog
RMVT-T-043 | P3 | 5 - Expansion | L5 - Business Intelligence | UX | Regulatory & ESG Reporting Dashboards | Visualization layer over the regulatory engine — surfaces compliance status, ESG metrics for sustainable trading reporting. | Dashboards align to current INEOS reporting cadence; supports drill-down to source trade; exports to required formats. | M | RMVT-T-030 | Backlog
RMVT-T-044 | P3 | 5 - Expansion | L1 - Data Collection | Connectors | Counterparty / Credit Signal Feeds | External credit data: CDS spreads, ratings actions, watchlists. Feeds counterparty risk scoring. | Credit signal updates flow into counterparty master; watchlist events surface in pre-trade check; CDS spread history charted. | M | RMVT-T-033 | Backlog
RMVT-T-045 | P3 | 5 - Expansion | L4 - AI/ML Models | ML Models | GenAI Trade Copilot v2 — Agentic Workflows | Move from Q&A to action — copilot proposes trade tickets, runs scenarios, drafts confirmations under human approval. | Trader can approve/reject proposed action; full audit log of agentic actions; rate limits to prevent runaway behavior. | XL | RMVT-T-026, RMVT-T-042 | Backlog

## PHASES
PHASED ROADMAP · 90-DAY PILOT + BEYOND
Phase | Window | Epics | Build Focus | Outcome at Phase End
1 - Foundation | Days 1–30 | 9 | Stand up trading-module API, multi-tenancy, TagTrack for instruments, lineage framework. Connect RightAngle + first market data. Build trade blotter + position store. | Sandbox alive with reconciled pilot-book data flowing end-to-end. No models yet.
2 - Pilot | Days 31–60 | 7 | Real-time P&L and position aggregation for pilot book. Physical-to-financial reconciliation engine. First AI model — optimal hedging — in trader-in-the-loop production. Trader Desk Dashboard v1. | Working AI model live for one trader. Baseline P&L and risk metrics captured.
3 - Scale | Days 61–90 | 10 | Add Endur/Allegro/exchange connectors. VaR + curve construction. Anomaly detection model. Middle Office dashboard. Contract corpus + GenAI Copilot v1. | Pilot book operationalized. Second book onboarded on same foundation. CoE blueprint defined.
4 - Harden | Days 91–180 | 12 | Monte Carlo VaR, Greeks, settlement engine, regulatory reporting. Forecasting + trade idea models. Counterparty master. News/AIS feeds. Event-impact scoring. C-suite briefing. Alert routing. | Production-grade across front, middle, and back office. Reg reporting live. Multiple AI models in production.
5 - Expansion | 180+ days | 7 | Voice/chat capture + transcript vectorization. Trader annotation UI. MLOps platform. Reg/ESG dashboards. Credit signal feeds. Agentic GenAI Copilot. | Standing AI Center of Excellence. Continuous model lifecycle. Trading floor operates with AI as embedded muscle.

## BY LAYER
ARCHITECTURE LAYER ROLLUP
Layer | Epics | Purpose | Capability Set
L1 - Data Collection | 10 | Capture every signal that moves the trade — market data, ETRM, vessels, counterparties, news. | • RightAngle / Endur / Allegro position feeds • Platts / Argus / Bloomberg market data • ICE / NYMEX FIX exchange connectors • AIS vessel tracking • News & sentiment feeds • Counterparty / credit signal feeds • Voice & chat capture
L2 - Data Lake | 6 | Structured + unstructured trading data unified — the memory that compounds the desk's edge. | • Time-series store for curves, vols, settlements • Trade blotter with full amendment lineage • Position history with molecule indexing • Counterparty master data • Contract corpus + vectorization (RAG) • Voice/chat transcripts vectorized
L3 - Analytics Engine | 8 | Radiant-MVT Core for trading — where reconciled data becomes the truth layer for front, middle, back office. | • Real-time P&L engine • Position aggregation service • VaR (parametric / historical / Monte Carlo) • Greeks calculator • Curve construction service • Settlement engine • Regulatory reporting (Dodd-Frank, EMIR, REMIT)
L4 - AI/ML Models | 9 | Intelligence at trader speed — six model families on Radiant-MVT-grade data, all explainable, all trader-in-loop. | • Optimal hedging recommendation • Anomaly detection / surveillance • GenAI Trade Copilot (RAG → agentic) • Forecasting (curves, basis, vol) • Trade idea generation • Event & sentiment impact scoring • Model lineage + MLOps
L5 - Business Intelligence | 6 | Decisions at the speed of the market — audience-specific lenses on the same reconciled core. | • Trader Desk Dashboard • Pre-trade margin & credit check • Middle Office & Risk Dashboard • C-Suite GenAI Briefing • Regulatory & ESG Reporting • Trader Annotation Capture
X - Cross-Cutting | 6 | Foundational platform capabilities every layer depends on. | • Trading-module API gateway • Multi-tenant data isolation • TagTrack™ extension for instruments • Audit & lineage framework • Physical-to-financial reconciliation engine • Alert routing & escalation

## DASHBOARD
BACKLOG DASHBOARD · COUNTS BY DIMENSION
BY PRIORITY |  | BY PHASE |  |  | BY LAYER
P0 — critical | 12 | 1 - Foundation | 9 |  | L1 - Data Collection | 10
P1 — high | 14 | 2 - Pilot | 7 |  | L2 - Data Lake | 6
P2 — medium | 12 | 3 - Scale | 10 |  | L3 - Analytics Engine | 8
P3 — low | 7 | 4 - Harden | 12 |  | L4 - AI/ML Models | 9
Total | 45 | 5 - Expansion | 7 |  | L5 - BI | 6
[5 empty] | X - Cross-Cutting | 6
BY EFFORT |  | BY WORKSTREAM |  |  | BY STATUS
S — ~1 week | 0 | Connectors | 10 |  | Backlog | 45
M — 2-4 weeks | 16 | Data Platform | 7 |  | In Progress | 0
L — 1-2 months | 26 | Analytics | 8 |  | In Review | 0
XL — 2-3 months | 3 | ML Models | 9 |  | Done | 0
|  | UX | 6 |  | Blocked | 0
|  | Platform/Infra | 5 |  | % Complete | 0%
CRITICAL PATH · P0 epics in Phase 1 (must ship before pilot)
RMVT-T-001 | Trading-Module API Gateway |  |  | L | —
RMVT-T-002 | Multi-Tenant Data Isolation for Trading Workspaces |  |  | L | RMVT-T-001
RMVT-T-003 | TagTrack™ Extension for Trading Instruments |  |  | XL | RMVT-T-002
RMVT-T-004 | Audit Trail & Lineage Framework |  |  | L | RMVT-T-002
RMVT-T-005 | RightAngle Position & Trade Connector |  |  | L | RMVT-T-003
RMVT-T-006 | Platts & Argus Market Data Connector |  |  | M | RMVT-T-001
RMVT-T-007 | Time-Series Store for Curves, Vols & Settlements |  |  | L | RMVT-T-001
RMVT-T-008 | Trade Blotter Store with Full Lineage |  |  | L | RMVT-T-003
RMVT-T-009 | Position History Store with Molecule Indexing |  |  | L | RMVT-T-003, RMVT-T-008